## Worklog_Feb22 (hidden)
PROJECT WORK LOG
| For the period covered: | 2021-06-01 | 2021-06-30
| Consultant Name | Vivek Sharma
Consultant's Company Name
| Client | Tiger Resort Leisure & Entertainment Inc.
| Client Manager | ALLAN LINDSEY LESCANO
sr.No. | Service Provided | Date mm/dd/yy | Total Hours Worked | Remarks
1 | Forex Selling Rate Top up issue (Gsystem sending blank balance ) handeled in Biztalk -Add the logic to get the node value -Add expressions to assign the values to parameter -Add expression to calculate cashless top up amount based on parameter value | 2022-02-01 | 8
2 | Forex Selling Rate | 2022-02-02 | 8
3 | Forex Selling Rate(Complete) Top up issue (Gsystem sending blank balance ) handeled in Biztalk Production Issue for accessing ESS and Self Service , on call discussion with Charm(Issue connecting AD) Restart host monitoring (1 H) | 2022-02-03 | 8+1
4 | OG Withdrawal Issue(Unable to view withdraw request from OG to DMS side)- Checked and updated with information and suggestions to integrate OG-DMS Prod ESS Login Error(32 less momery issue)- freed up run time memory (1 h) | 2022-02-04 | 8
| On call discussion with Dexter for safe keeping withdrwal api and sharing details with ISJ with sample request and response | 2022-02-06 | 1
5 | Ge Latest card from Paymaya, random test and share with team. Discussion with Nikki and Dennis for Admin portal email sending, Shared staff info enquery api with dennis | 2022-02-07 | 8
6 | Checking ISJ issue for Halo Points(Free Play, Base Points) to slot bonus credit Bigfour login issue, (accesstoken expired) Metting with Gallagher for HALO_Gallagher integration(1 H) BizTalk Authetication api deplouyment 1. Database table has been deployed in DB 2. IIS Application has been created on all 4 server 3. Configuration of IIS service for app pool has been completed by Datasec 4. BizTalk Supporting dll (Total of 10) has been copied and installed in GAC for 30 & 31 server 5. Configuration entry has been updated in BizTalk Config File for 30 & 31 Server 6. Custom behavior configuration has been done in machine config file on 30 & 31 server 7. BizTalk interface (Mobile App for access token, Property website for login & OTP validation, Property Website for Resend OTP ) has been deployed on BizTalk server. 8. A new BizTalk host instance Online Gaming has been created and configured for all 4 servers with the help of Ces. 9. Log file location has been created on archive location for above interfaces. 10. Receive location, Send Ports and Orchestration is configured for archive location, BizTalk DB, Halo universal service and Halo DB. | 2022-02-08 | 13 | Deployment
7 | Deployment Continue Testing Pin Validation Issue encountering to validate access token Compared QA and Prod dependancy classes and dll's Access to DMZ server fized with data sec(30 min) | 2022-02-09 | 15
8 | Testing Pin validation with correct PIN Chcek on Dennis issue for Evoucher and Evoucher notification after deployment(30 min) | 2022-02-10 | 8
9 | BizTalk Deployment Discussion with Dennis (Application & Interface)(1) Meeting [OG] Withdrawal function with QA(30 min) | 2022-02-11 | 8
10 | Meeting Biztalk Task Prioritization(30 min) Large Payout Flow - Online Slots DMS Issue, Wrong format of request(30 min) Fixed the issue in IIS servicefor evoucher (1 H) Not Sending Withdrawal Request Status to Biztalk, no request received from DMS(30 min) | 2022-02-14 | 8
11 | Testing and deployment of safe keeping transfer to okash and safekeeping Tx History date changes on 205 (2 H) OG API list completion after comparing with ISJ list (30 min) Meeting with BigFour and troubleshooting session for One time top-up. (2 H) Meeting with OG iSlot - Joint Test Session (30 min) Meeting with JH and MAX for OG large payout api.(30 min) Discussion with Leandro for issue OMA200640, get the table for withdrawal and status corresponding to db entry code. Need to update store procedure to include Withdrawal in my request.(30 min) Deployment pkg and document for Resend OTP and Send OTP Interface (1.5 H) Reply to Dennis Email for Admin Portal & provided him the send email code with configuration values.(30 min) Check on the issue for withdrawal after DMS approval(30 min) | 2022-02-15 | 8.5
12 | Update store procedure to include Withdrawal in my request, testing .(1 H) Testing OG Top-Up with Maris for issue, Coordinate with Max for the issue. (1 h) Testing of Withdrawal with Chelle, Records are not reflected in G-System. UEC confirmed for receiving cancel request for Tx. After approval DMS response has different approval status than what is configured in BT and BT push a cancel request. Already notify to DMS to pass correct format. (1H) Investigating DMS Withdrawal Issue, Transaction does not exist in G-System as there was an error in first step to call withdrawal request. Current Interface creates a DMS record before calling G-system. Need to modify the logic to first get response from G-system and if transaction status success only then create DMS ticket otherwise just respond the error to calling system.(2 H) Discussion with EJ for OG deploye interface security.(20 Min) Deployment of interface (Resend (SMS) OTP, send OTP, Patron Profile Information, Patron Point Balance), IIS services on server 30 (2.5H) Discussion with Kathy for unmatched transactions in Admin portal (Need development in Payment gateway api), Service fee in Withdrawal, Contact update(30 min) | 2022-02-16 | 8.5
13 | Update safekeeping Withdrawal interface , change the logic to create dms record only if g-system response is success . (1.5 h) Update Canon withdrawal interface to accept status “Withdrawal Completed”. (1 H) Discussion with EJ for OG related api security at iis.(30 Min) Deployment of interface (Resend (SMS) OTP, send OTP, Patron Profile Information, Patron Point Balance), IIS services on server 31\32\33 (2 H). Deploy DB table and data for Halo Points Mapping (30 min) Deployment pkg for (FreePlay/CirclePoint History, Convert Free Play/ Circle Points to Table Bonus Credit, Reset PIN(Update and forget, DMS Patron PIN Updat, UpdateContact (Dependency for Update PIN), My Request) (2 h Deployment of interface (FreePlay/CirclePoint History, Convert Free Play/ Circle Points to Table Bonus Credit,My Request )on server 30. (2 H) | 2022-02-17 | 9
14 | Deployment and configuration of interface (FreePlay/CirclePoint History, Convert Free Play/ Circle Points to Table Bonus Credit, My Request, Patron Contact Update, PatronPINUpdate), IIS services on server 30-33 ( 5 H). Deploy DB Store Proc sp_CreateUpdateContactUpdateOTP, sp_CreateUpdatePINOTP (15 min) Testing and Troubleshooting session with QA (2 H) Deployment Pkg for (Safekeeping withdrawal, Okash withdrawal, cashless topup, Forex selling rate)(1 H) | 2022-02-18 | 8
15 | Deployment and configuration of interface (SafeKeeping Withdrawal, Okash Withdrawal, DMS Safekeeping Withdrawal/OkashWithdrawal, Large Payout, DMS Large Payout, Forex Selling Rate, Cashless Top up) & IIS services on server 30-33 ( 7.5H). Discussion with Peachy for Payment gateway (30 min) | 2022-02-21 | 8
16 | Okash transaction history date issue fixed and testing (2 H) DMS Cashless Withdrawal Workflow Issues for no name display investigation. Reported to Bigfour to pass name in request.(30 min) On Phone call with PM for pending task allocation and task prioritization(45 min) Fixing deployment GetHaloComps project into 205 server issues. Still pending as need to redeploy the interface from old msi.(1 H) Large Payout development to integrate with ISJ API (4 H) | 2022-02-22 | 8
17 | Large Payout development to integrate with ISJ API , Testing and deployment in 205 server(5 H) Investigate OG pending transaction and card expiry issue reported by Peachy. Shared BizTalk logs, directed ISj to pass 2 digit in month & reported issue to be investigate why OG showing error while opening PayMaya page. (1H) BizTalk installation on DMZ servers.(1.5 H) Prod issue for AD phone update, Shared logs and issue details and process for team to resolve the issue(30 min) | 2022-02-23 | 8
18 | QA Issue Biztalk Error Messages in OMA with Kathy(30 Min) Shared Large payout API for DMs with details ( 1 H) Created a temporary sql job to clear pending payment transactions for smother testing by QA and ISJ(1 H) Discussion with Carmie for Adding new email for Telco-AD integration no email notification(30 min) OMA200644: Incorrect Withdrawal Date issue fix with Michelle(1.5 H) Large Payout testing session(30 min) Discussion with Peachy for payment gateway automated processor (30 min) Void Payment development(3.5 H) | 2022-02-24 | 8
|  | 2022-02-25 | 0
| Total Days/Hours |  | 151 |  |  | 4%
| CONSULTANT SIGNATURE | Vivek Sharma |  |  | Date:
| CLIENT SIGNATURE | ALLAN LINDSEY LESCANO |  |  | Date:
Information Technology
[Internal Use Only]
______________________________________________ Verified By:
|  |  | 2017-01-24 | 2017-02-23
|  |  | 2017-02-24 | 2017-03-23
|  |  | 2017-03-24 | 2017-04-23
|  |  | 2017-04-24 | 2017-05-23
|  |  | 2017-05-24 | 2017-06-23
|  |  | 2017-06-24 | 2017-07-23

## Worklog_July2023
PROJECT WORK LOG
For the period covered:
| Consultant Name | Vivek Sharma
Consultant's Company Name
| Client | Tiger Resorts Leisure & Entertainment Inc.
Client Manager
Sr. No. | Service Provided | Change Request Number Reference (to be identified by IT Finance) | Ringi Number Reference (to be identified by IT Finance) | Cost Type (to be filled up by PMO/Consultant) | Affected Systems (to be filled by PMO/Consultant) | Date dd/mm/yy | Hours Worked For Each Activity | Amount | Remarks
1 | Team track import data |  |  | Capex | Team Track | 2023-07-02 | 0.5 |  |  |  | 1
2 | Gcash reload issue, Inestigation and detail log |  |  | Opex | OOC | 2023-07-03 | 2 |  |  |  | 2
3 | Patron registartion status update testing |  |  | Capex | Patron Registartion | 2023-07-03 | 4 |  |  |  | 3
4 | UKG PIT Manager Development |  |  | Capex | VR | 2023-07-03 | 2 |  |  |  | 4
5 | Discussion with CY for Gcash reload issue and adjusting the time out period to make it longer in case of INIt status receied from Gcash |  |  | Opex | OOC | 2023-07-04 | 1 |  |  |  | 2
6 | Shared information for DMZ ports used in Gcash, Coordinated with Bonz |  |  | Opex | OOC | 2023-07-04 | 1 |  |  |  | 2
7 | Meeting with Xtendly for OMA |  |  | Capex | OMA | 2023-07-04 | 2 |  |  |  | 5
8 | UKG PIT Manager Development |  |  | Capex | VR | 2023-07-04 | 2 |  |  |  | 4
9 | Meeting with Dangel-AutoTable Sync Issue |  |  | Opex | AutoTable | 2023-07-05 | 0.5 |  |  |  | 2
10 | DMS Email update issue investigation, The response from HALO has an error code attached |  |  | Opex | OMA | 2023-07-05 | 2 |  |  |  | 2
11 | One time payment share with Jonas create sample request and response Process flow for paymet to top up |  |  | Capex | OMA | 2023-07-05 | 2 |  |  |  | 5
12 | UKG PIT Manager Development |  |  | Capex | VR | 2023-07-05 | 3.5 |  |  |  | 4
13 | Meeting with app support gamin -Biztalk DB - housekeeping |  |  | Opex | BizTalk | 2023-07-06 | 1 |  |  |  | 2
14 | Discussion with carmie for creating AX job in production to dump full xml shared with VR, sap |  |  | Capex | Team Track | 2023-07-06 | 1 |  |  |  | 1
15 | Import employee leaves issue, Date format in file is wrong, Discussion with Jaie for the date change Tested after chnages applied -error out, file contains wrong data need more investigation |  |  | Capex | Team Track | 2023-07-06 | 6 |  |  |  | 6
16 | Discussion with Justin for staff info service using card id, Shared Staff enhance service, shared request response and documnetation. |  |  | Capex | OMA | 2023-07-07 | 1 |  |  |  | 5
17 | UKG PIT Manager Development |  |  | Capex | VR | 2023-07-07 | 7 |  |  |  | 4
18 | Import Employee photo, staff data , skills and leaves in team track |  |  | Capex | Team Track | 2023-07-10 | 1 |  |  |  | 6
19 | Discussion with app support for prod contact update, Shared request /response to HALO |  |  | Opex | OMA | 2023-07-10 | 1 |  |  |  | 2
20 | Pit Manager Development |  |  | Capex | VR | 2023-07-10 | 6 |  |  |  | 4
21 | Pit Manager Development Unit testing Chcek logs in PMIT |  |  | Capex | VR | 2023-07-11 | 8 |  |  |  | 4
22 | Pit Manager Development chnages and unit testing |  |  | Capex | VR | 2023-07-12 | 4 |  |  |  | 4
23 | Testing Pit manager with PMIT for Open /close table, employee swipe |  |  | Capex | VR | 2023-07-12 | 4 |  |  |  | 7
24 | Maya Wallet-safekeeping issue troubleshooting in QA -Chcek issue -Applying fixes and restesing |  |  | Capex | OOC | 2023-07-13 | 5 |  |  |  | 1
25 | PIT manager QA testing |  |  | Capex | VR | 2023-07-13 | 2 |  |  |  | 7
26 | Discussion with CY for Gcash processor timeout update when response stuck in INIt status, Update configuration in prod |  |  | Capex | OOC | 2023-07-13 | 1 |  |  |  | 1
27 | Prod setup for teamtrack staff import with carmie to set the ax batch job, testing using newly xml dump Data |  |  | Capex | Team Track | 2023-07-14 | 2 |  |  |  | 1
28 | QA PIT manager set up to PM Unit testing Share error with Jaie Change temp uri as discussed and tested in soap UI stillerror out |  |  | Capex | VR | 2023-07-14 | 3 |  |  |  | 7
29 | Run immage import in Production and check team track db updates |  |  | Capex | Team Track | 2023-07-14 | 1 |  |  |  | 6
30 | Meeting with OMA, shared mobile /eail update API, safekeeping balance api details |  |  | Capex | OMA | 2023-07-14 | 2 |  |  |  | 5
31 | Testing PIT manager in QA setup with PMIT worked Setup with PM does not sybc data and no logs |  |  | Capex | VR | 2023-07-17 | 4 |  |  |  | 7
32 | Share API's with sample to Xtendly -Gcash top up to cashless -Safekeeping transaction history, safekeeping to okash Cashless transaction history |  |  | Capex | OMA | 2023-07-17 | 2 |  |  |  | 5
33 | Maya Wallet-safekeeping issue troubleshooting in QA |  |  | Capex | OOC | 2023-07-17 | 2 |  |  |  | 8
34 | Maya Wallet-safekeeping issue troubleshooting in QA |  |  | Capex | OOC | 2023-07-18 | 5.5 |  |  |  | 8
35 | Gcash safekeeping timeline updates |  |  | Capex | OOC | 2023-07-18 | 0.5 |  |  |  | 1
36 | Discussion with xendly for Slot bonus credit Share api details with sample -Slot bonus credit Slot bonus history |  |  | Capex | OMA | 2023-07-18 | 2 |  |  |  | 5
37 | Meeting with Riel-Gcash Discussion |  |  | Opex | OOC | 2023-07-19 | 0.5 |  |  |  | 2
38 | Production issue -investigate Pin management -AX emp verify was error out -tested with new emp id worked |  |  | Opex | ESS | 2023-07-19 | 2 |  |  |  | 2
39 | PayMaya Safekeeping Top up Development |  |  | Capex | OOC | 2023-07-19 | 5.5 |  |  |  | 9
40 | OMA Joint QAT |  |  | Capex | OMA | 2023-07-20 | 2 |  |  |  | 5
41 | PIT manager testing -share soap request and response with Jaie -Discussion with Jaie for pass jason request for testing -did not worked |  |  | Capex | VR | 2023-07-20 | 3 |  |  |  | 7
42 | PayMaya Safekeeping Top up Development |  |  | Capex | OOC | 2023-07-20 | 3 |  |  |  | 9
43 | Discussion with Bonxz for Gcash INIT issue and time adjustment for timeout period |  |  | Opex | OOC | 2023-07-21 | 1 |  |  |  | 2
44 | PayMaya Safekeeping Top up Development |  |  | Capex | OOC | 2023-07-21 | 7 |  |  |  | 9
45 | Gcash safekeeping topup Development |  |  | Capex | OOC | 2023-07-24 | 7.5 |  |  |  | 10
46 | Csn list for charging station |  |  | Opex | Carrging Station | 2023-07-25 | 1 |  |  |  | 2
47 | G cash top up for init transaction, transaction status change to complete for previous manually credited transaction |  |  | Opex | OOC | 2023-07-25 | 0.5 |  |  |  | 2
48 | Autovallet qa deployment |  |  | Capex | AutoVallet | 2023-07-25 | 3 |  |  |  | 11
49 | Employees email extract discussion |  |  | Capex | SAP | 2023-07-25 | 0.5 |  |  |  | 1
50 | Gcash safekeeping topup - map safekeeping top up res to gcash resp, safekeeping to dms |  |  | Capex | OOC | 2023-07-25 | 3 |  |  |  | 10
51 | Discussion with Rimmon, network and Gilbert for CRM qa issue |  |  | Capex | Sugar CRM | 2023-07-26 | 0.5 |  |  |  | 1
52 | Meeting -SAP SF AD Business Email |  |  | Capex | SAP | 2023-07-26 | 1 |  |  |  | 1
53 | Discussion with xtendly and share api details with request and response |  |  | Capex | OMA | 2023-07-26 | 1 |  |  |  | 5
54 | slot bonus credit testing after receiving 0 balance from uec to share with oma |  |  | Capex | OMA | 2023-07-26 | 1 |  |  |  | 5
55 | Prod Gcash issue check reported by Reil, Connection was broke and restored. Monitoing nee success transactions |  |  | Opex | OOC | 2023-07-26 | 1 |  |  |  | 2
56 | Gcash safekeeping topup |  |  | Capex | OOC | 2023-07-26 | 3.5 |  |  |  | 10
57 | Autovallet Joint testing , Shared error response recived in BizTalk with gordon. |  |  | Capex | AutoVallet | 2023-07-27 | 1 |  |  |  | 1
58 | Discussion with justine for slot converion |  |  | Capex | OMA | 2023-07-27 | 0.5 |  |  |  | 5
59 | Gcash safekeeping topup |  |  | Capex | OOC | 2023-07-27 | 6.5 |  |  |  | 10
60 | uat session for PIT manager |  |  | Capex | VR | 2023-07-28 | 2 |  |  |  | 7
61 | Discussion with Reil for WangPOS duplicate awarding issue fix and time lines, VR-CSn integration, Autovallet QA testing |  |  | Capex | Wang POS | 2023-07-28 | 1 |  |  |  | 1
62 | Gcash safekeeping topup |  |  | Capex | OOC | 2023-07-28 | 5 |  |  |  | 10
63 | Discussion for pin validation count for oma with mic Worked with riel for processing gcash failed transactions Email from ad |  |  | Capex | Team Track | 2023-07-31 | 5 |  |  |  | 5
| Total Days/Hours | [5 empty] | 163
| CONSULTANT SIGNATURE |  |  |  |  | Vivek Sharma |  |  |  | Date:
| CLIENT SIGNATURE |  |  |  |  | ALLAN LINDSEY LESCANO |  |  |  | Date:
Information Technology
[Internal Use Only]
______________________________________________ Verified By:

## Manhour per Day
Date | Total Hours Worked
2023-07-02 | 0.5
2023-07-03 | 8
2023-07-04 | 6
2023-07-05 | 8
2023-07-06 | 8
2023-07-07 | 8
2023-07-10 | 8
2023-07-11 | 8
2023-07-12 | 8
2023-07-13 | 8
2023-07-14 | 8
2023-07-17 | 8
2023-07-18 | 8
2023-07-19 | 8
2023-07-20 | 8
2023-07-21 | 8
2023-07-24 | 7.5
2023-07-25 | 8
2023-07-26 | 8
2023-07-27 | 8
2023-07-28 | 8
2023-07-31 | 5
Grand Total: | 163

## Suporting Document
Cut-off:
Highlights Summary: | Project/Support | Worklog # | Start Date | End Date | % Completion | Status
BizTalk QA support | Project | 1,14,24,26,27,35,49,51,52,57,61 | 2023-07-02
Production Support | Support | 2, 5,6,9,10,13,19,37,38,43,46,47,55 | 2023-07-03
Patron registartion status update testing | Project | 3 | 2023-07-03 | 2023-07-03 | 100%
UKG PIT Manager Development | Project | 4, 8,12,17,20,21,22 | 2023-07-03 | 2023-07-12 | 100%
OMA related Tasks | Project | 7, 11,16,30,32,36,40,53,54,58,63 | 2023-07-04 | 2023-07-31
Team Track Testing | Project | 15,18,29 | 2023-07-06 | 2023-07-14 | 100%
UKG Pit Manager Testing | Project | 23,25,28,31,41,60 | 2023-07-12 | 2023-07-28 | 100%
Maya Wallet-safekeeping issue troubleshooting in QA | Support | 33,34 | 2023-07-17 | 2023-07-18 | 100%
PayMaya Safekeeping Top up Development(Debit/Credit) | Project | 39,42,44 | 2023-07-19 | 2023-07-21 | 100%
Gcash safekeeping topup Development | Project | 45,50,56,59,62 | 2023-07-24 | 2023-07-28 | 100%
Autovallet qa deployment | Project | 48 | 2023-07-25 | 2023-07-25 | 100%

## Performance Tracker
No. | Task | Type | Estimated Effort (hours) | Estimated Effort (days) | Actual Effort (Hours) Billable | Actual Effort (Days) Billable | Start Date | End Date | Delivery Date | Delivery Variance | Effort Variance | Status | Remarks | Worklog Ref#
1 | BizTalk QA support | Project | 22 | 2.75 | 14 | 1.75 | 2023-07-02 | 2023-07-28 | 2023-07-28 | 0 | -8 | Completed | On-track | 1,14,24,26,27,35,49,51,52,57,61 | 11
2 | Production Support | Support | 26 | 3.25 | 14.5 | 1.8125 | 2023-07-03 | 2023-07-26 | 2023-07-26 | 0 | -11.5 | Completed | On-track | 2, 5,6,9,10,13,19,37,38,43,46,47,55 | 13
3 | Patron registartion status update testing | Project | 4 | 0.5 | 4 | 0.5 | 2023-07-03 | 2023-07-03 | 2023-07-03 | 0 | 0 | Completed | On-track | 3 | 1
4 | UKG PIT Manager Development | Project | 28 | 3.5 | 32.5 | 4.0625 | 2023-07-03 | 2023-07-07 | 2023-07-12 | 5 | 4.5 | Completed | Priority on support related task has delayed the delivery. | 4, 8,12,17,20,21,22 | 7
5 | OMA related Tasks | Project | 22 | 2.75 | 20.5 | 2.5625 | 2023-07-04 | 2023-07-31 | 2023-07-31 | 0 | -1.5 | Completed | On-track | 7, 11,16,30,32,36,40,53,54,58,63 | 11
6 | Team Track Testing | Project | 12 | 1.5 | 8 | 1 | 2023-07-06 | 2023-07-14 | 2023-07-14 | 0 | -4 | Completed | On-track | 15,18,29 | 3
7 | UKG Pit Manager Testing | Project | 24 | 3 | 18 | 2.25 | 2023-07-12 | 2023-07-15 | 2023-07-28 | 13 | -6 | Completed | Delayed delivery due to priority support | 23,25,28,31,41,60 | 6
8 | Maya Wallet-safekeeping issue troubleshooting in QA | Support | 2 | 0.25 | 7.5 | 0.9375 | 2023-07-17 | 2023-07-17 | 2023-07-18 | 1 | 5.5 | Completed | Troubleshooting takes time for the resource to complete | 33,34 | 2
9 | PayMaya Safekeeping Top up Development(Debit/Credit) | Project | 12 | 1.5 | 15.5 | 1.9375 | 2023-07-19 | 2023-07-21 | 2023-07-21 | 0 | 3.5 | Completed | On-track | 39,42,44 | 3
10 | Gcash safekeeping topup Development | Project | 20 | 2.5 | 25.5 | 3.1875 | 2023-07-24 | 2023-07-27 | 2023-07-28 | 1 | 5.5 | Completed | More time needed to finish the development | 45,50,56,59,62 | 5
11 | Autovallet qa deployment | Project | 4 | 0.5 | 3 | 0.375 | 2023-07-25 | 2023-07-25 | 2023-07-25 | 0 | -1 | Completed | On-track | 48 | 1
163
Formulas:
End Date = [Start Date]+ROUND([Estimated Effort (days)],0)